## program_impact_data
country | quarter | year | producers_trained | workshops_delivered | adoption_rate_pct | quality_improvement_pts | technical_visits | investment_usd | satisfaction_score
Brazil | Q1 | 2024 | 200 | 5 | 15 | 1.2 | 150 | 58500 | 4.3
Brazil | Q2 | 2024 | 400 | 10 | 35 | 2.8 | 350 | 78000 | 4.5
Brazil | Q3 | 2024 | 600 | 15 | 55 | 4.5 | 550 | 98000 | 4.6
Brazil | Q4 | 2024 | 800 | 20 | 75 | 6.2 | 750 | 106000 | 4.7
Colombia | Q1 | 2024 | 120 | 3 | 12 | 1 | 100 | 42000 | 4.2
Colombia | Q2 | 2024 | 250 | 6 | 30 | 2.5 | 220 | 52000 | 4.4
Colombia | Q3 | 2024 | 380 | 9 | 50 | 4 | 380 | 63000 | 4.6
Colombia | Q4 | 2024 | 500 | 12 | 72 | 5.8 | 480 | 68000 | 4.7
Peru | Q1 | 2024 | 80 | 2 | 10 | 0.8 | 70 | 35000 | 4
Peru | Q2 | 2024 | 180 | 5 | 28 | 2 | 160 | 45000 | 4.2
Peru | Q3 | 2024 | 300 | 8 | 48 | 3.8 | 280 | 58000 | 4.4
Peru | Q4 | 2024 | 400 | 10 | 68 | 5.2 | 380 | 62000 | 4.5
Honduras | Q1 | 2024 | 60 | 2 | 8 | 0.6 | 50 | 28000 | 3.9
Honduras | Q2 | 2024 | 140 | 4 | 22 | 1.8 | 130 | 38000 | 4.1
Honduras | Q3 | 2024 | 240 | 6 | 42 | 3.5 | 220 | 48000 | 4.3
Honduras | Q4 | 2024 | 300 | 8 | 65 | 5 | 280 | 52000 | 4.5

## Overview
Program Name: Coffee Quality Enhancement Program
Duration: 12 months (Jan 2024 - Dec 2024)
Countries: Brazil, Colombia, Peru, Honduras
Total Budget: USD 500,000
Target Beneficiaries: 2,000 coffee producers
Key Components:
1. Training & Capacity Building
2. Technical Assistance & Field Support
3. Quality Lab Equipment
PROGRAM CONTEXT This Excel workbook contains the complete project plan, budget, and monitoring framework for the Coffee Quality Enhancement Program—a 12-month initiative supporting 2,000 coffee producers across Brazil, Colombia, Peru, and Honduras. The program focuses on improving post-harvest coffee quality through training, technical assistance, and laboratory equipment installation. This workbook serves as the primary project management tool for coordinating activities, tracking expenditures, and measuring impact. | PROGRAM MONITORING DATA - Monthly progress on activities - Actual expenditures vs. planned budget - Producer participation numbers - Quality improvement measurements (cupping scores) PURPOSE: Track real-time implementation and adjust plans
"This book integrates data from multiple sources: 1. PROGRAM DESIGN DATA - Activity schedules and timelines - Budget allocations by component and country - Target beneficiary numbers - Component definitions (Training, Technical Assistance, Equipment) PURPOSE: Establish baseline plan and resource allocation 2. FAOSTAT DATABASE (External - UN Food and Agriculture Organization) - Historical coffee production data by country (tonnes) - Used to estimate realistic capacity improvement targets - Accessible at: www.fao.org/faostat PURPOSE: Set evidence-based production targets 3. WORLD BANK OPEN DATA (External) - Agricultural employment rates (% of workforce) - Rural population growth rates - Investment indicators (% of GDP) - Used to contextualize program within country development trends - Accessible at: data.worldbank.org" | "What does 70% adoption rate mean?" → Out of 100 producers trained, 70 are actually using the new practices → This is good! Industry average is 50-60% "Why does Brazil get 35% of the budget?" → Brazil serves 40% of total producers (800 out of 2,000) → Larger scale = more workshops, more field visits, more equipment "What is 'quality improvement' measured in points?" → Coffee quality is scored 0-100 by professional cuppers (Q Graders) → +5 points = noticeable difference in taste, higher price for farmers → +5.8 points actual = exceeded target! "Is 100% budget utilization good or bad?" → GOOD! It means we spent exactly what we planned → Not overspending = responsible with donor funds → Not underspending = we delivered full program as promised

## Gantt
Task ID | Task Name | Start Date | End Date | Duration | Jan | Feb | Mar | April | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Manager
1 | Project Kickoff | 2025-01-06 | 2025-01-10 | 4 | [12 empty] | E1 TEAM
2 | Baseline Assessment | 2025-01-13 | 2025-01-14 | 1 | [12 empty] | E1 TEAM
3 | Training Module Development | 2025-01-15 | 2025-01-24 | 0 | [12 empty] | E2 TEAM
4 | Procurement - Lab Equipment | 2025-01-27 | 2025-02-01 | 5 | [12 empty] | E3 TEAM
5 | Training Delivery - Brazil | 2025-02-03 | 2025-02-28 | 25 | [12 empty] | E2 TEAM
6 | Training Delivery - Colombia | 2025-03-03 | 2025-03-28 | 25 | [12 empty] | E2 TEAM
7 | Training Delivery - Peru | 2025-04-07 | 2025-04-25 | 18 | [12 empty] | E2 TEAM
8 | Training Delivery - Honduras | 2025-05-05 | 2025-03-28 | 38 | [12 empty] | E2 TEAM
9 | Technical Assistance (ongoing) | 2025-01-27 | 2025-05-30 | 123 | [12 empty] | E3 TEAM
10 | Lab Installation | 2025-06-09 | 2025-07-15 | 36 | [12 empty] | E3 TEAM
11 | Mid-term Evaluation | 2025-08-04 | 2025-08-29 | 25 | [12 empty] | E1 TEAM
12 | Final Assessment | 2025-09-01 | 2025-09-26 | 25 | [12 empty] | E1,E3 TEAM
13 | Report & Lessons Learned | 2025-11-03 | 2025-11-15 | 12 | [12 empty] | E1,E2,E3 TEAM

## Budget
SPEBUDGET BREAKDOWN BY COMPONENT
Component | Budget USD | % of Total | Q1 2025 | Q2 2025 | Q3 2025 | Q4 2025 | Total Spent | Variance | Status
Training and Capacity Building | 200000 | 40% | 30000 | 60000 | 70000 | 40000 | 200000 | 0 | On Track
Technical Assistance | 175000 | 34% | 20000 | 40000 | 60000 | 50000 | 170000 | 5000 | Under budget
Quality Lab Equipment | 125000 | 26% | 10000 | 50000 | 55000 | 15000 | 130000 | -5000 | Over budget
Total | 500000 | 1 | 60000 | 150000 | 185000 | 105000 | 500000 | 0 | On Track
BUDGET BY COUNTRY
Country | Training | Tech Assist | Equipment | Total | % of Total | Producers Reached | Cost per producer
Brazil | 70000 | 60000 | 45000 | 175000 | 0.35 | 0.97222 | 180000
Colombia | 50000 | 45000 | 30000 | 125000 | 0.25 | 0.96154 | 130000
Peru | 45000 | 40000 | 25000 | 110000 | 0.22 | 1.0476 | 105000
Honduras | 35000 | 30000 | 25000 | 90000 | 0.18 | 0.51429 | 175000
TOTAL | 200000 | 175000 | 125000 | 500000 | 1 | 3.4957 | 590000
DETAILED LINE ITEMS
Category | Item Description | Unit Cost | Quantity | Total | Country | Quarter | Budget Line
Training | Workshop facilitation (per day) | 500 | 120 | 60000 | ALL | Q1-Q4 | Training
Training | Training materials & handouts | 15 | 2000 | 30000 | ALL | Q1-Q2 | Training
Training | Venue rental (per workshop) | 800 | 50 | 40000 | ALL | Q2-Q3 | Training
Training | Travel & accommodation trainers | 2000 | 35 | 70000 | ALL | Q2-Q4 | Training
Technical Assistance | Field visits (per producer) | 50 | 20 | 1000 | ALL | Q2-Q4 | Tech Assist
Technical Assistance | Agronomist fees (monthly) | 3000 | 12 | 36000 | ALL | Q2-Q4 | Tech Assist
Technical Assistance | Quality testing & analysis | 25 | 825 | 20625 | ALL | Q3-Q4 | Tech Assist
Technical Assistance | Follow-up support calls | 10 | 900 | 9000 | ALL | Q3-Q4 | Tech Assist
Equipment | Moisture meters | 200 | 100 | 20000 | ALL | Q2 | Equipment
Equipment | Sample roasters | 2500 | 12 | 30000 | ALL | Q2-Q3 | Equipment
Equipment | Cupping tables & equipment | 5000 | 8 | 40000 | ALL | Q2-Q3 | Equipment
Equipment | Storage facilities improvement | 7000 | 5 | 35000 | ALL | Q3 | Equipment

## KPI Tracker
KEY PERFORMANCE INDICATORS - MONTHLY TRACKING
Indicator | Target | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Actual | % Achievement | Status
Number of producers trained | 2000 | 0 | 50 | 150 | 300 | 500 | 700 | 1000 | 1300 | 1600 | 1800 | 1950 | 2000 | 11350 | 17.62% | ⚠ At Risk
Number of workshops delivered | 50 | 0 | 5 | 8 | 12 | 18 | 25 | 32 | 40 | 45 | 48 | 50 | 50 | 333 | 15.02% | ⚠ At Risk
% producers adopting improved practices | 70 | 0 | 0 | 0 | 10 | 35 | 40 | 50 | 58 | 65 | 68 | 70 | 72 | 468 | 14.96% | ✓ Achieved
Number of technical assistance visits | 2000 | 0 | 0 | 0 | 100 | 300 | 500 | 700 | 950 | 1200 | 1500 | 1800 | 2000 | 9050 | 22.1% | ✓ Achieved
Quality labs installed | 12 | 0 | 0 | 0 | 0 | 2 | 4 | 8 | 10 | 12 | 12 | 12 | 12 | 72 | 16.67% | ✓ Achieved
Average quality score improvement (cupping) | 5 | 0 | 0 | 0 | 0 | 1.2 | 2.5 | 3.5 | 4.2 | 4.8 | 5.2 | 5.5 | 5.8 | 32.7 | 15.29% | ✓ Achieved
% budget spent vs planned | 100 | 12 | 24 | 36 | 48 | 60 | 72 | 82 | 88 | 92 | 96 | 98 | 100 | 808 | 12.38% | ✓ Achieved
COUNTRY-LEVEL KPIs
Country | Producers Trained | WorkShops | Adoption Rate | Quality Improvement | Satisfaction Score | Budget Utilization
Brazil | 800 | 20 | 75% | 6.2 pts | 4.5/5.0 | 98%
Colombia | 500 | 12 | 72% | 5.8 pts | 4.6/5.0 | 100%
Peru | 400 | 10 | 68% | 5.2 pts | 4.3/5.0 | 99%
Honduras | 300 | 8 | 65% | 5.0 pts | 4.4/5.0 | 97%
AVERAGE | 2000 | 50 | 280% | 0 | 0 | 394%

## Risk Register
Risk ID | Risk Description | Probability | Impact | Risk Score | Mitigation Strategy | Status
RO1 | Weather delays field activities | High | Medium | 6 | Build 2-week buffer in schedule | Active
RO2 | Equipment delivery delays | Medium | High | 6 | Order 3 months in advance | Mitigate
RO3 | Low producer participation | Low | High | 3 | Community leaders engagement | Monitores
RO4 | Currency fluctuation affects budget | Medium | Medium | 4 | 10% contingency fund | Active
RO5 | Staff turnover mid-project | Low | Medium | 2 | Knowledge documentation & backup plans | Monitored
References
RO1 Risk Score | 2 |  |  |  | Nivel | Valor
RO2 Risk Score | 2 |  |  |  | High | 3
RO3 Risk Score | 1 |  |  |  | Medium | 2
RO4 Risk Score | 4 |  |  |  | Low | 1
RO5 Risk Score | 2